Project Planning Phase

Project Planning

| Date | 27/09/2026 |
| --- | --- |
| Team ID | SWTID-2026-8900 |
| Project Name | Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designe |

1. Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Request Submission | USN-1 | As an employee, I can submit a standard laptop request by providing my department, location, and required date. | 3 | High | Team |
| Sprint-1 | Request Submission | USN-2 | As an employee, I can select a standard laptop model from the approved catalog. | 2 | High | Team |
| Sprint-1 | Request Submission | USN-3 | As an employee, I can view the estimated cost of the selected laptop before submitting the request. | 2 | Medium | Team |
| Sprint-1 | User Management | USN-4 | As an employee, I can access the procurement request form using my organizational account. | 2 | High | Team |
| Sprint-1 | Request Validation | USN-5 | As the system, I can validate the submitted laptop request to ensure all mandatory information is provided. | 2 | High | Team |
| Sprint-1 | Request Tracking | USN-6 | As an employee, I can view the current status of my laptop request. | 2 | High | Team |
| Sprint-2 | Approval Workflow | USN-7 | As a manager, I can receive a notification when a laptop request requires my approval. | 2 | High | Team |
| Sprint-2 | Approval Workflow | USN-8 | As a manager, I can approve or reject a laptop request with comments. | 3 | High | Team |
| Sprint-2 | Approval Workflow | USN-9 | As the system, I can automatically route approved requests to the next stage of the procurement workflow. | 3 | High | Team |
| Sprint-2 | Flow Designer Automation | USN-10 | As the system, I can automatically trigger the procurement workflow when a standard laptop request is submitted. | 3 | High | Team |
| Sprint-2 | Notifications | USN-11 | As an employee, I can receive notifications when my request is submitted, approved, rejected, or completed. | 2 | Medium | Team |
| Sprint-2 | Procurement | USN-12 | As a procurement team member, I can view approved laptop requests that are ready for procurement. | 2 | High | Team |
| Sprint-3 | Procurement Processing | USN-13 | As a procurement team member, I can assign an approved laptop request to a supplier or procurement task. | 3 | High | Team |
| Sprint-3 | Procurement Processing | USN-14 | As a procurement team member, I can update the procurement status of a laptop order. | 2 | High | Team |
| Sprint-3 | Inventory | USN-15 | As an IT administrator, I can check whether the requested standard laptop is available in inventory. | 3 | High | Team |
| Sprint-3 | Inventory | USN-16 | As an IT administrator, I can update laptop inventory when a device is assigned to an employee. | 3 | High | Team |
| Sprint-3 | Delivery | USN-17 | As an employee, I can view the expected delivery status of my laptop. | 2 | Medium | Team |
| Sprint-3 | Audit & Tracking | USN-18 | As an administrator, I can view the complete history of a laptop request from submission to completion. | 3 | High | Team |
| Sprint-4 | Dashboard | USN-19 | As an administrator, I can view a dashboard showing pending, approved, rejected, and completed laptop requests. | 3 | Medium | Team |
| Sprint-4 | Reporting | USN-20 | As a procurement manager, I can generate a report of laptop orders and procurement activity. | 3 | Medium | Team |
| Sprint-4 | Automation | USN-21 | As the system, I can automatically update the request status after each workflow stage is completed. | 3 | High | Team |
| Sprint-4 | Exception Handling | USN-22 | As the system, I can notify the appropriate team when a request cannot be processed automatically. | 2 | Medium | Team |
| Sprint-4 | Testing | USN-23 | As a project team member, I can test the complete laptop procurement workflow from request submission to delivery. | 3 | High | Team |
| Sprint-4 | Deployment | USN-24 | As an administrator, I can deploy the completed automated procurement workflow for actual use. | 3 | High | Team |

Sprint-wise allocation

| Sprint | Main Focus | Story Points |
| --- | --- | --- |
| Sprint-1 | Request Submission, Validation & Tracking | 13 |
| Sprint-2 | Approval, Flow Designer Automation & Notifications | 15 |
| Sprint-3 | Procurement, Inventory, Delivery & Audit | 16 |
| Sprint-4 | Dashboard, Reporting, Testing & Deployment | 17 |
| Total | Complete Project | 61 |

2. Project Tracker, Velocity & Burndown Chart

For consistency with your template, we can use a 6-day sprint and a planned capacity of approximately 20 story points per sprint.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 05 Oct 2026 | 10 Oct 2026 | 20 | 10 Oct 2026 |
| Sprint-2 | 20 | 6 Days | 12 Oct 2026 | 17 Oct 2026 | 20 | 17 Oct 2026 |
| Sprint-3 | 20 | 6 Days | 19 Oct 2026 | 24 Oct 2026 | 18 | 26 Oct 2026 |
| Sprint-4 | 20 | 6 Days | 27 Oct 2026 | 01 Nov 2026 | 20 | 01 Nov 2026 |

Sprint focus

Sprint-1 – Request Foundation

- Employee request form

- Laptop catalog

- Request validation

- Request status tracking

- User access

Sprint-2 – Workflow Automation

- Manager approval

- Automated request routing

- Flow Designer workflow

- Notifications

- Procurement queue

Sprint-3 – Procurement & Inventory

- Procurement processing

- Supplier assignment

- Inventory checking

- Device assignment

- Delivery tracking

- Audit history

Sprint-4 – Management & Deployment

- Dashboard

- Reports

- Exception handling

- End-to-end testing

- Deployment

3. Velocity Calculation

Your template gives the example:

Team velocity = 20 story points per sprint
Sprint duration = 10 days

The formula is:

Average Velocity per Day = Total Story Points ÷ Sprint Duration

For your project:

Average Velocity = 20 ÷ 6

Average Velocity = 3.33 story points/day

Therefore:

Team Average Velocity = 3.33 story points per day

For four sprints, if the team completes 20 points in each sprint:

Total Velocity = 20 + 20 + 20 + 20 = 80 story points

Average Sprint Velocity = 80 ÷ 4 = 20 story points/sprint

4. Burndown Chart

A burndown chart shows how much work remains in a sprint over time. At the beginning of the sprint, the remaining work is high. As tasks are completed, the remaining story points decrease toward zero.

For your project, you can use 20 story points as the planned work for each sprint.

Sprint-1 Burndown Data

| Day | Planned Remaining Story Points | Actual Remaining Story Points |
| --- | --- | --- |
| Day 1 | 20 | 20 |
| Day 2 | 17 | 18 |
| Day 3 | 14 | 14 |
| Day 4 | 10 | 11 |
| Day 5 | 5 | 6 |
| Day 6 | 0 | 0 |

Sprint-2 Burndown Data

| Day | Planned Remaining Story Points | Actual Remaining Story Points |
| --- | --- | --- |
| Day 1 | 20 | 20 |
| Day 2 | 17 | 18 |
| Day 3 | 14 | 15 |
| Day 4 | 10 | 10 |
| Day 5 | 5 | 5 |
| Day 6 | 0 | 0 |

Sprint-3 Burndown Data

Since Sprint-3 completed 18 out of 20 points, two points remained at the planned end date.

| Day | Planned Remaining Story Points | Actual Remaining Story Points |
| --- | --- | --- |
| Day 1 | 20 | 20 |
| Day 2 | 17 | 18 |
| Day 3 | 14 | 15 |
| Day 4 | 10 | 11 |
| Day 5 | 5 | 7 |
| Day 6 | 0 | 2 |

Sprint-4 Burndown Data

| Day | Planned Remaining Story Points | Actual Remaining Story Points |
| --- | --- | --- |
| Day 1 | 20 | 20 |
| Day 2 | 17 | 18 |
| Day 3 | 14 | 14 |
| Day 4 | 10 | 9 |
| Day 5 | 5 | 5 |
| Day 6 | 0 | 0 |

5. Short Description for Your Report

You can place this below the tables:

Product Backlog, Sprint Schedule and Estimation

The product backlog for the project Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designer contains the functional requirements required to automate the standard laptop procurement process. The backlog is divided into user stories covering request submission, approval, workflow automation, notifications, procurement, inventory, delivery tracking, reporting, and deployment. Each user story is assigned story points according to its complexity and a priority based on its importance to the system.

The project is divided into four sprints. Sprint 1 focuses on creating the laptop request and validation process. Sprint 2 focuses on approval and Flow Designer automation. Sprint 3 focuses on procurement, inventory, delivery, and audit tracking. Sprint 4 focuses on dashboard development, reporting, testing, and deployment.

Project Tracker, Velocity and Burndown Chart

The project tracker is used to monitor the progress of each sprint by comparing planned story points with completed story points. The team's average velocity is approximately 20 story points per sprint, or 3.33 story points per day for a six-day sprint. The burndown chart represents the remaining work throughout each sprint and helps the team identify delays and ensure that the planned work is completed within the sprint duration.